## 00_Lisez-moi
Lisez-moi
Donnees generiques. Effort en JH ; Build ponctuel et Run en JH/mois. Cout par fournisseur alternatif ; ne pas additionner les alternatives. Bleu : saisies, noir : calculs, vert : liens, jaune : hypotheses a confirmer.
Cle | Valeur
title | Synthetic web service estimate
date | 2026-10-07
currency | EUR
effort_unit | JH
notes | Entirely synthetic public acceptance example, not a quote. Standard selected; Provider A is a provisional illustration. Build JH and Run JH/month are separate. Provider alternatives must not be added. Forecast FinOps savings require measurement. Kubernetes: Non applicable after suitability review; managed runtime selected. Taxes, discounts, FX and growth excluded; non-cloud OPEX assumed zero. Capacity overloads and delivery overload remain open; this is not an approved production design.

## 01_Hypotheses
Hypotheses
Scenario global et facteurs editables. Les prix synthetiques doivent etre remplaces par des sources datees.
Hypothese | Valeur | Unite | Statut | Source | Notes
scenario_global | Standard | scenario | Confirme | SYN-01 | Global scenario; task overrides take precedence.
taux_journalier | 650 | EUR/JH | A confirmer | SYN-01 | Illustrative rate; replace before a real estimate.
mois_par_an | 12 | mois/an | Confirme | SYN-01 | Annualisation factor.
hours_per_jh | 8 | h/JH | A confirmer | SYN-01 | Editable convention; task estimates already in JH.
schedule.foundation_available | 6 | JH | A confirmer | SYN-01 | Period 1; collective capacity across Foundation roles, not per-role capacity. Owner: delivery lead. Dependency TASK-01 before TASK-02/09/10; individual role availability remains unverified.
schedule.foundation_overload | 3 | JH | A confirmer | SYN-01 | Dynamic formula: Foundation Build minus available JH; positive = overload, DEC-SCHEDULE.
capacity.production.Standard.base.cpu | 6 | vCPU | A confirmer | SYN-01 | Assumed aligned CPU demand; independent service scenario and workload band.
capacity.production.Standard.high.cpu | 12 | vCPU | A confirmer | SYN-01 | Assumed high-band CPU demand, not a benchmark.
capacity.production.Standard.base.memory | 8 | GiB | A confirmer | SYN-01 | Synthetic working-set demand; per runtime unit 8 GiB.
capacity.production.Standard.base.storage_gib | 100 | GiB | A confirmer | SYN-01 | Shared usable data demand; backend capacity 200 GiB, not replica-scaled.
capacity.production.Standard.base.iops | 1000 | operations/s | A confirmer | SYN-01 | Shared backend assumed effective 2000 operations/s; latency/mix unmeasured.
capacity.production.Standard.base.bandwidth | 100 | Mbit/s | A confirmer | SYN-01 | Shared link assumed 200 Mbit/s effective; egress envelope is separate pricing.
capacity.production.Standard.base.concurrency | 100 | requests | A confirmer | SYN-01 | Runtime assumed safe 100 concurrent requests/unit; no throughput inferred.
capacity.production.Standard.base.utilisation_target | 0.75 | ratio | A confirmer | SYN-01 | CPU/memory/concurrency target, includes headroom; shared backend requires independent checks.
capacity.production.Standard.base.scaling_limit | 3 | instances | A confirmer | SYN-01 | Hypothetical ceiling; does not make high-band demand feasible.
capacity.production.Standard.base.failure_domain_reserve | 1 | instances | A confirmer | SYN-01 | One runtime loss; does not prove zone/region DR.
capacity.production.Standard.cpu_per_unit | 4 | vCPU/instance | A confirmer | SYN-01 | Effective capacity assumption, not hardware specification.
capacity.production.Standard.units | 2 | instances | A confirmer | SYN-01 | Standard runtime count corresponds to COMP-03 and Provider A Standard cost quantity.
capacity.production.Standard.high.overload_ratio | 2 | ratio | A confirmer | SYN-01 | Dynamic: high demand / effective CPU at target; >1 infeasible. Other dimensions and failure event require measurement.
contradiction.old_units | 1 | instances | A confirmer | SYN-01 | SYN-02 older single-replica statement; same workload scope.
contradiction.selected_units | 2 | instances | A confirmer | SYN-01 | SYN-03 later resilience requirement; provisional selected branch in DEC-CONFLICT.
contradiction.unit_price | 45 | EUR/instance/month | A confirmer | SYN-01 | Provider A synthetic unit price; not an official tariff.
contradiction.cloud_delta | 45 | EUR/mois | A confirmer | SYN-01 | Dynamic selected minus old runtime cost; excludes common envelope/non-production.
contradiction.build_old | 1 | JH | A confirmer | SYN-01 | Single-replica infrastructure branch; mutually exclusive, not included as another task.
contradiction.build_selected | 3 | JH | A confirmer | SYN-01 | Selected infrastructure branch equals TASK-01 Standard net JH.
contradiction.build_delta | 2 | JH | A confirmer | SYN-01 | Dynamic selected minus old Build.
contradiction.run_old | 0.5 | JH/mois | A confirmer | SYN-01 | Old branch monthly operations forecast.
contradiction.run_selected | 1 | JH/mois | A confirmer | SYN-01 | Selected monthly operations equals TASK-06 Standard.
contradiction.run_delta | 0.5 | JH/mois | A confirmer | SYN-01 | Dynamic selected minus old monthly Run.
finops.baseline | 90 | EUR/mois | A confirmer | SYN-01 | Forecast: Development and Staging always-on, two units at Provider A price. No measured billing.
finops.savings_low_fraction | 0.25 | ratio | A confirmer | SYN-01 | Conservative forecast; retains on-demand wakeup.
finops.savings_high_fraction | 0.5 | ratio | A confirmer | SYN-01 | Selected illustrative schedule; recurring costs already include this schedule, do not subtract savings twice.
finops.savings_low | 22.5 | EUR/mois | A confirmer | SYN-01 | Dynamic baseline times low saving fraction.
finops.savings_high | 45 | EUR/mois | A confirmer | SYN-01 | Dynamic baseline times high saving fraction.
finops.savings_selected | 45 | EUR/mois | A confirmer | SYN-01 | Dynamic baseline minus scheduled Provider A Standard non-production charges.
tco_horizon_years | 3 | years | A confirmer | SYN-01 | Equal scope and constant demand; taxes, FX, discounts and growth excluded.
non_cloud_opex | 0 | EUR/mois | A confirmer | SYN-01 | Explicit synthetic absence, not an unknown represented as zero.
comparison_scenario | Standard | scenario | A confirmer | SYN-01 | Same reference scenario for all provider TCOs; independent of scenario_global, task overrides still apply.
tco.ProviderA.Standard | 41906 | EUR/3years | A confirmer | SYN-01 | Dynamic selected Build plus 36 months of human Run, Provider A Standard cloud and non-cloud OPEX; alternatives never added.
tco.ProviderB.Standard | 42446 | EUR/3years | A confirmer | SYN-01 | Dynamic same-perimeter Provider B comparison; Build, human Run, cloud and horizon remain separate in Scenarios.
tco.ProviderC.Standard | 42986 | EUR/3years | A confirmer | SYN-01 | Dynamic same-perimeter Provider C comparison; alternatives never added.
region_eligibility | A/B/C: hypothetical single-region eligibility; multi-region DR unverified | scope | A confirmer | SYN-01 | No real provider or regional suitability claim.
commercial_policy | No commitments, same currency, invented prices, no discounts | scope | A confirmer | SYN-01 | Runtime quotes and region eligibility required before approval.
weighted_criteria | Operational fit 50%, recovery evidence 30%, TCO 20%; unscored until evidence | scope | A confirmer | SYN-01 | No invented suitability scores.
source_write_policy | owner-only | policy | A confirmer | SYN-01 | Synthetic migration; generator performs no source/environment mutations.

## 02_Inventaire
Inventaire
Inventaire generique des composants et environnements.
ID | Composant | Environnement | Quantite | Unite | Notes
COMP-01 | Web service | Development | 1 | service | Synthetic development workload.
COMP-02 | Web service | Staging | 1 | service | Synthetic validation workload.
COMP-03 | Web service | Production | 2 | replica | Synthetic runtime workload.
COMP-04 | Managed data and platform services | Production | 1 | platform envelope | Usable data, backups, network/egress, logging, registry/build and support; synthetic envelope pricing, not a SKU quote.

## 03_Architecture
Architecture
Options d'architecture et decisions techniques a justifier.
ID | Composant | Type | Environnement | Fournisseur | Decision | Notes
ARCH-01 | Web service | Managed application | Production | Provider A | Managed runtime | Provisional Standard: two runtime replicas. Economique: one, Resilient: three. High workload overload remains open. See DEC-CONFLICT and capacity assumptions.
ARCH-02 | Managed data and platform services | Managed backend | Production | Provider A | Managed backend, separate shared capacity | COMP-04; shared data capacity is not multiplied by runtime replicas. Backup and restore evidence required.
Diagram nodes
ID | Composant | Environnement | Zone | Fournisseur
COMP-01 | Web service | Development | Application | Provider A
COMP-02 | Web service | Staging | Application | Provider A
COMP-03 | Web service | Production | Application | Provider A
COMP-04 | Managed data and platform services | Production | Data | Provider A
Diagram flows
ID | Source | Destination | Flux
FLOW-01 | COMP-03 | COMP-04 | HTTPS (SYN-03)
Icon provenance
Fournisseur | Source officielle | Licence / marque | Fichier | SHA-256
provider-neutral |  | Original neutral labelled symbols
Diagram manifest
JSON | {"edge_ids": ["FLOW-01"], "icon_provenance": [], "icon_sources": ["provider-neutral"], "node_ids": ["COMP-01", "COMP-02", "COMP-03", "COMP-04"], "output_hashes": {"png": "b974403dc6b60ce6ee2807f5d4d4c7c2f97f39c3f271e86d5c77631bec2a8012", "svg": "dc33f5574f3991d64fc15713506792ead06eec47d5dd3d9e4591835ca27e8042"}, "warnings": []}

## 04_Taches_JH
Taches_JH
Estimations en JH. Economique = bas, Standard = probable, Resilient = haut. Override local prioritaire ; Build et Run se lisent separement.
ID | Lot | Domaine | Tache | Livrable | Environnement | Role | Prerequis | Dependances | Critere d'acceptation | Preuve attendue | JH bas | JH probable | JH haut | Scenario retenu | Scenario override | JH retenu | Nature | Couverture | Source | Confiance | Notes
TASK-01 | Foundation | infrastructure | Provision isolated environments | Infrastructure definitions | All | Platform engineer | Approved inventory |  | Three environments provisioned | Deployment report | 2 | 3 | 5 | Standard |  | 3 | Build | Partial, evidenced synthetic coverage | SYN-01 | Medium | Gross 3/4/6 JH; covered 1/1/1 JH (SYN-02); net 2/3/5 JH. One canonical owner; no aliases.
TASK-02 | Foundation | server-hardening | Apply security baseline | Baseline policy | All | Security engineer | Environments available | TASK-01 | Baseline checks pass | Control report | 1 | 2 | 4 | Resilient | Resilient | 4 | Build | Full | SYN-01 | Medium | Explicit task override.
TASK-03 | Delivery | cicd-devsecops | Configure delivery pipeline | Pipeline definitions | All | Delivery engineer | Source repository | TASK-01 | Promote and rollback demonstrated | Pipeline run | 2 | 3 | 5 | Standard |  | 3 | Build | Full | SYN-01 | Medium | Synthetic task.
TASK-04 | Delivery | hosting-capacity | Validate runtime capacity | Capacity report | Staging | Performance engineer | Deployable service | TASK-03 | Staging harness records base/high CPU, memory, storage, IOPS, bandwidth and concurrency; verify target and overload before approval | Synthetic load assumptions now; measured traces, latency percentiles and saturation report required for approval | 1 | 2 | 3 | Standard |  | 2 | Build | Full | SYN-01 | Low | Capacity target to confirm.
TASK-05 | Operations | cloud-migration | Rehearse service transition | Transition runbook | Production | Platform engineer | Validation complete | TASK-02, TASK-04 | Recovery demonstrated | Rehearsal record | 1 | 2 | 4 | Standard |  | 2 | Build | Full | SYN-01 | Medium | Synthetic transition only. Preparation, transfer, integrity, cutover, rollback and owner-only decommissioning in runbook; hypercare is a separate recurring operation. No live source access.
TASK-06 | Operations | finops | Review recurring usage | Usage review | Production | Operations engineer | Usage evidence | TASK-05 | Waste actions recorded | Monthly review | 0.5 | 1 | 2 | Standard |  | 1 | Run | Full | SYN-01 | Medium | Recurring effort in JH/month; kept separate from Build.
TASK-07 | Operations | finops | Schedule non-production runtime | Reversible schedule | All | Platform engineer | Approved inventory | TASK-05 | Forecast; compare metered usage before/after at equal scope; restore always-on schedule on validation failure | Reversible schedule with SYN-01 assumptions | 1 | 2 | 3 | Standard |  | 2 | Build | Full | SYN-01 | Medium | Synthetic net additional Build; one owner and no duplicate deliverable.
TASK-08 | Delivery | architecture-diagram | Reconcile inventory and explicit flows | Embedded diagram and flow register | All | Platform engineer | Approved inventory | TASK-03 | Each node matches inventory; HTTPS edge matches SYN-03; no inferred connection | Embedded diagram and flow register with SYN-01 assumptions | 0.5 | 1 | 2 | Standard |  | 1 | Build | Full | SYN-01 | Medium | Synthetic net additional Build; one owner and no duplicate deliverable.
TASK-09 | Foundation | cloud-architecture | Resolve managed runtime versus cluster suitability | Architecture decision | All | Platform engineer | Approved inventory | TASK-01 | Confirm application isolation, backup and recovery evidence; cluster work excluded because no platform requirement | Architecture decision with SYN-01 assumptions | 0.5 | 1 | 2 | Standard |  | 1 | Build | Full | SYN-01 | Medium | Synthetic net additional Build; one owner and no duplicate deliverable.
TASK-10 | Foundation | provider-selection | Compare equal service scope and three-year TCO | Provider comparison | All | Platform engineer | Approved inventory | TASK-01 | Nine equal-scope alternatives, regional eligibility remains hypothetical; do not approve without official dated quotes | Provider comparison with SYN-01 assumptions | 0.5 | 1 | 2 | Standard |  | 1 | Build | Full | SYN-01 | Medium | Synthetic net additional Build; one owner and no duplicate deliverable.

## 05_Couts_cloud
Couts_cloud
Coûts recurrents par option fournisseur et scenario ; tarifs synthetiques non contractuels. Le multiplicateur convertit l'unite en mois.
ID | Fournisseur | Service | Environnement | Scenario | Unite | Quantite | Prix unitaire (EUR) | Devise | Multiplicateur mensuel | Cout mensuel (EUR) | Cout annuel (EUR) | Source | Confiance | Notes | Statut prix
COST-01 | Provider A | Managed runtime | Production | Economique | unit/month | 1 | 45 | EUR | 1 | 45 | 540 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-02 | Provider A | Managed runtime scheduled (Development + Staging) | Non-production | Economique | unit/month | 2 | 45 | EUR | 0.5 | 45 | 540 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-03 | Provider A | Managed data, backups, network/egress, logging, build/registry, support | Production | Economique | unit/month | 1 | 24 | EUR | 1 | 24 | 288 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-04 | Provider A | Managed runtime | Production | Standard | unit/month | 2 | 45 | EUR | 1 | 90 | 1080 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-05 | Provider A | Managed runtime scheduled (Development + Staging) | Non-production | Standard | unit/month | 2 | 45 | EUR | 0.5 | 45 | 540 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-06 | Provider A | Managed data, backups, network/egress, logging, build/registry, support | Production | Standard | unit/month | 1 | 36 | EUR | 1 | 36 | 432 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-07 | Provider A | Managed runtime | Production | Resilient | unit/month | 3 | 45 | EUR | 1 | 135 | 1620 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-08 | Provider A | Managed runtime scheduled (Development + Staging) | Non-production | Resilient | unit/month | 2 | 45 | EUR | 0.5 | 45 | 540 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-09 | Provider A | Managed data, backups, network/egress, logging, build/registry, support | Production | Resilient | unit/month | 1 | 60 | EUR | 1 | 60 | 720 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-10 | Provider B | Managed runtime | Production | Economique | unit/month | 1 | 50 | EUR | 1 | 50 | 600 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-11 | Provider B | Managed runtime scheduled (Development + Staging) | Non-production | Economique | unit/month | 2 | 50 | EUR | 0.5 | 50 | 600 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-12 | Provider B | Managed data, backups, network/egress, logging, build/registry, support | Production | Economique | unit/month | 1 | 24 | EUR | 1 | 24 | 288 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-13 | Provider B | Managed runtime | Production | Standard | unit/month | 2 | 50 | EUR | 1 | 100 | 1200 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-14 | Provider B | Managed runtime scheduled (Development + Staging) | Non-production | Standard | unit/month | 2 | 50 | EUR | 0.5 | 50 | 600 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-15 | Provider B | Managed data, backups, network/egress, logging, build/registry, support | Production | Standard | unit/month | 1 | 36 | EUR | 1 | 36 | 432 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-16 | Provider B | Managed runtime | Production | Resilient | unit/month | 3 | 50 | EUR | 1 | 150 | 1800 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-17 | Provider B | Managed runtime scheduled (Development + Staging) | Non-production | Resilient | unit/month | 2 | 50 | EUR | 0.5 | 50 | 600 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-18 | Provider B | Managed data, backups, network/egress, logging, build/registry, support | Production | Resilient | unit/month | 1 | 60 | EUR | 1 | 60 | 720 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-19 | Provider C | Managed runtime | Production | Economique | unit/month | 1 | 55 | EUR | 1 | 55 | 660 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-20 | Provider C | Managed runtime scheduled (Development + Staging) | Non-production | Economique | unit/month | 2 | 55 | EUR | 0.5 | 55 | 660 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-21 | Provider C | Managed data, backups, network/egress, logging, build/registry, support | Production | Economique | unit/month | 1 | 24 | EUR | 1 | 24 | 288 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-22 | Provider C | Managed runtime | Production | Standard | unit/month | 2 | 55 | EUR | 1 | 110 | 1320 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-23 | Provider C | Managed runtime scheduled (Development + Staging) | Non-production | Standard | unit/month | 2 | 55 | EUR | 0.5 | 55 | 660 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-24 | Provider C | Managed data, backups, network/egress, logging, build/registry, support | Production | Standard | unit/month | 1 | 36 | EUR | 1 | 36 | 432 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-25 | Provider C | Managed runtime | Production | Resilient | unit/month | 3 | 55 | EUR | 1 | 165 | 1980 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-26 | Provider C | Managed runtime scheduled (Development + Staging) | Non-production | Resilient | unit/month | 2 | 55 | EUR | 0.5 | 55 | 660 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer
COST-27 | Provider C | Managed data, backups, network/egress, logging, build/registry, support | Production | Resilient | unit/month | 1 | 60 | EUR | 1 | 60 | 720 | SYN-01 | Low | Synthetic forecast only; same service perimeter, alternative provider. Replace envelope by verified SKU breakdown before real use. | A confirmer

## 06_Scenarios
Scenarios
Comparaison sans overrides locaux. Le rapprochement technique additionne JH Build et JH Run/mois, des unites incompatibles : utilisation budgetaire interdite.
Scenario | Description | Rapprochement technique (non budgetaire) | JH Build | JH Run/mois | Notes
Economique | Minimum suitable scope | 10 | 9.5 | 0.5 | Uses low JH.
Standard | Expected delivery scope | 18 | 17 | 1 | Uses likely JH.
Resilient | Higher resilience and uncertainty | 32 | 30 | 2 | Uses high JH.
Comparaison fournisseurs - scenario de reference et horizon dans Hypotheses
Fournisseur | Build (JH) | Run humain (JH/mois) | Cloud (EUR/mois) | Horizon (annees) | TCO (EUR)
Provider A | 19 | 1 | 171 | 3 | 41906
Provider B | 19 | 1 | 186 | 3 | 42446
Provider C | 19 | 1 | 201 | 3 | 42986

## 07_Phasage
Phasage
Lots et jalons. Le rapprochement technique additionne JH Build et JH Run/mois, des unites incompatibles : utilisation budgetaire interdite.
Phase | Sequence | Jalon | Rapprochement technique (non budgetaire) | JH Build | JH Run/mois | Notes
Foundation | 1 | Environments ready | 9 | 9 | 0 | Baseline before delivery.
Delivery | 2 | Service validated | 6 | 6 | 0 | Capacity before transition.
Operations | 3 | Transition complete | 5 | 4 | 1 | Run effort displayed separately.

## 08_Risques
Risques
Incertitudes, impacts et actions de reduction du risque.
ID | Risque | Impact | Probabilite | Mitigation | Responsable | Statut
RISK-01 | Unknown traffic profile | Capacity assumptions may change | Medium | Measure representative load | Performance engineer | Open
RISK-OVERLOAD | High workload CPU exceeds Standard target capacity | Service target infeasible at high band; limited scaling and failure reserve | Assumed | TASK-04 measurement; revisit replicas, quotas and placement before approval | Performance engineer | Open
RISK-SCHEDULE | Foundation delivery overload | Dependent delivery cannot meet provisional period | Certain under forecast | DEC-SCHEDULE; role owner replans capacity before approval | Platform engineer | Open
RISK-FINOPS | Scheduled runtime unavailable during unplanned testing | Wakeup delay | Medium | Retain on-demand wakeup and reversible always-on schedule | Operations engineer | Open

## 09_Arbitrages
Arbitrages
Decisions explicites et hypotheses a confirmer.
ID | Question | Option | Justification | Statut | Source
DEC-01 | Runtime hosting option | Managed runtime | Reduce operational burden | A confirmer | SYN-01
DEC-CONFLICT | SYN-02 single replica conflicts with SYN-03 two replicas | Provisional two-replica branch | Owner: architecture lead; resolve before design approval. See contradiction.* calculation cells for Build, monthly Run and cloud deltas. Single-replica branch accepts outage; only selected branch enters tasks. All three service scenarios keep the same perimeter. | Provisional | SYN-02; SYN-03
DEC-FINOPS | Reduce forecast non-production idle costs | Reversible 50% runtime scheduling forecast | Savings range and selected saving are dynamic finops.* cells. TASK-07 Build and TASK-06 monthly Run. Roll back schedule if wakeup affects testing; meter usage before/after at equal scope. Savings unvalidated; scheduled cost already reflects them. | Forecast, unvalidated | SYN-01
DEC-ARCH | Managed runtime or Kubernetes platform | Managed runtime and shared managed backend | No cluster requirement in this synthetic scope; Kubernetes work Non applicable. Retain application isolation and restore evidence; managed runtime reduces platform ownership, operator monthly Run remains explicit. | Provisional | SYN-01
DEC-SCHEDULE | Foundation Build exceeds Period 1 capacity | Move dependent Foundation work into another period before approval | Dynamic schedule.foundation_overload compares all Foundation Build with collective capacity, not a per-role budget. Delivery lead must confirm collective and individual role availability; subsequent periods cannot start before prerequisites. No approved calendar until overload is resolved. | Open | SYN-01

## 10_Sources
Sources
References datees ; les exemples synthetiques ne constituent pas des tarifs de marche.
ID | Titre | Type | Date | URL | Notes
SYN-01 | Synthetic public assumptions | Synthetic | 2026-10-07 |  | No client data and no live tariff claims.
SYN-02 | Earlier synthetic single-replica brief and coverage evidence | Synthetic | 2026-10-01 |  | Invented conflicting requirement and coverage; no private source.
SYN-03 | Later synthetic resilience requirement and flow register | Synthetic | 2026-10-07 |  | Invented two-replica requirement; FLOW-01 COMP-03 to COMP-04 HTTPS. No live topology.

## 11_Synthese
Synthese
Synthese dynamique des charges et options cloud. Les prix, la couverture et les incertitudes doivent etre confirmes avant engagement.
Indicateur | Valeur | Unite | Notes
Rapprochement technique (Build + Run/mois) | 20 | Unites mixtes | Utilisation budgetaire interdite : JH Build et JH Run/mois ont des unites incompatibles.
JH Build | 19 | JH | Effort ponctuel.
JH Run mensuel | 1 | JH/mois | Effort recurrent.
Cout Build | 12350 | EUR | Effort Build au taux journalier saisi.
Cout Run mensuel | 650 | EUR/mois | Effort Run au taux journalier saisi.
Cloud mensuel ¦ Provider A ¦ Economique | 114 | EUR/mois | Option alternative ; ne pas sommer les fournisseurs.
Cloud mensuel ¦ Provider A ¦ Standard | 171 | EUR/mois | Option alternative ; ne pas sommer les fournisseurs.
Cloud mensuel ¦ Provider A ¦ Resilient | 240 | EUR/mois | Option alternative ; ne pas sommer les fournisseurs.
Cloud mensuel ¦ Provider B ¦ Economique | 124 | EUR/mois | Option alternative ; ne pas sommer les fournisseurs.
Cloud mensuel ¦ Provider B ¦ Standard | 186 | EUR/mois | Option alternative ; ne pas sommer les fournisseurs.
Cloud mensuel ¦ Provider B ¦ Resilient | 260 | EUR/mois | Option alternative ; ne pas sommer les fournisseurs.
Cloud mensuel ¦ Provider C ¦ Economique | 134 | EUR/mois | Option alternative ; ne pas sommer les fournisseurs.
Cloud mensuel ¦ Provider C ¦ Standard | 201 | EUR/mois | Option alternative ; ne pas sommer les fournisseurs.
Cloud mensuel ¦ Provider C ¦ Resilient | 280 | EUR/mois | Option alternative ; ne pas sommer les fournisseurs.
Statut finance | Taux journalier renseigne - approbation non acquise | Controle | Un taux inconnu bloque couts humains, TCO et approbation financiere, pas les capacites ou JH. Un taux renseigne ne vaut pas approbation.